## sudheer
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimated Time | Adjustment Estimate | Status
1 | Drink&Delight:1 | 1 | Test Cases Template |  | 2020-08-03 | 1 hr | 2 hrs | Completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hr | 1.5 hrs | Completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | Completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 1.5 hrs
|  | 5 | Use Case Diagram |  | 2020-08-04 | 1 hr
|  | 6 | Sequence Diagram |  | 2020-08-04 | 1 hr
2 | Drink&Delight:2 | 1 | Creating a Spring boot starter project |  |  | 0.5 hr
|  | 2 | Adding dependencies in Pom.xml and initializing it |  |  | 1 hr
|  | 3 | Adding server, jpa and logging properties in application.properties |  |  | 1 hr
3 | Drink&Delight:3 | 1 | Add Vendor Details | Dao Layer |  | 3 hrs
|  |  |  | Service Layer |  | 3 hrs
|  |  |  | Entity Layer |  | 3 hrs
4 | Drink&Delight:4 | 1 | Edit and search vendor details | Dao Layer |  | 3 hrs
|  |  |  | Service Layer |  | 3 hrs
|  |  |  | Service implemntation |  | 3 hrs
5 | Drink&Delight:5 | 1 | populate the data in database |  |  | 3 hrs
|  | 2 | check data and valdiations using postman server |  |  | 2 hrs
2 hrs